## WBSData
ID | Nombre | Inicia | Termina | Duracion | Entregables | Fecha de entrega | Responsables
1 | Proyecto Hotel | 2020-03-13 13:00 | 2020-04-14 17:00 | 33 dias | Historias de usuario | 2020-03-17 | Ibet Ortiz, Daniel Trujillo
1.1 | Analisis | 2020-03-13 13:00 | 2020-03-18 17:00 | 6 dias | Requerimientos | 2020-03-17 | Luis Romero, Aldo Torres
1.1.1 | Topicos (Historias de usuario) | 2020-03-13 13:00 | 2020-03-14 17:00 | 2 dias | Arquitectura | 2020-03-19 | Daniel Nolasco
1.1.2 | Requerimientos | 2020-03-15 13:00 | 2020-03-16 17:00 | 2 dias | Prototipo de tecnologia | 2020-03-23 | Luis Romero, Daniel Nolasco, Aldo Diaz, Ibet Ortiz
1.1.3 | Arquitectura | 2020-03-17 13:00 | 2020-03-18 17:00 | 2 dias | Prototipo de manejo de hilos | 2020-03-23 | Daniel Nolasco
1.2 | Diseño | 2020-03-19 13:00 | 2020-04-30 17:00 | 10 dias | Prototipo de metodos de comunicación | 2020-03-26 | Aldo Diaz
1.2.1 | Servidor | 2020-03-19 13:00 | 2020-03-26 17:00 | 8 dias | Prototipo de servidor bidireccional | 2020-03-30 | Luis Romero
1.2.1.1 | Eleccion de tecnologias (Sockets o RMI) | 2020-03-19 13:00 | 2020-03-20 17:00 | 2 dias | Prototipo de implementacion de un protocolo | 2020-03-30 | Daniel Nolasco
1.2.1.1.1 | Prototipo de tecnologia a usar | 2020-03-19 13:00 | 2020-03-20 17:00 | 2 dias | Prototipo de programa en un hilo de ejec. | 2020-03-31 | Aldo Diaz
1.2.1.2 | Prototipo de manejo de hilos | 2020-03-21 13:00 | 2020-03-22 17:00 | 2 dias | Servidor | 2020-04-13 | Luis Romero, Daniel Nolasco, Aldo Diaz
1.2.1.3 | Prototipo de metodos de comunicacion | 2020-03-23 13:00 | 2020-03-24 17:00 | 2 dias | Simulador | 2020-04-13 | Luis Romero, Daniel Nolasco, Aldo Diaz
1.2.1.4 | Prototipo de un servidor bidireccional | 2020-03-25 13:00 | 2020-03-26 17:00 | 2 dias | Cliente | 2020-04-13 | Luis Romero, Daniel Nolasco, Aldo Diaz
1.2.2 | Simulador | 2020-03-27 13:00 | 2020-04-30 17:00 | 4 dias | Pruebas de servidor (Documentacion) | 2020-04-14 | Ibet Ortiz, Daniel Trujillo
1.2.2.1 | Prototipo de implementacion de un protocolo | 2020-03-27 13:00 | 2020-03-28 17:00 | 2 dias | Pruebas de simulador (Documentacion) | 2020-04-14 | Ibet Ortiz, Daniel Trujillo
1.2.2.2 | Prototipo de un programa en un hilo de ejecucion | 2020-03-29 13:00 | 2020-03-30 17:00 | 2 dias | Pruebas de cliente (Documentacion) | 2020-04-14 | Ibet Ortiz, Daniel Trujillo
1.3 | Desarrollo | 2020-03-31 13:00 | 2020-04-11 17:00 | 12 dias
1.3.1 | Servidor | 2020-03-31 13:00 | 2020-04-03 17:00 | 4 dias
1.3.2 | Simulador | 2020-04-04 13:00 | 2020-04-07 17:00 | 4 dias
1.3.3 | Cliente | 2020-04-08 13:00 | 2020-04-11 17:00 | 4 dias
1.4 | Pruebas | 2020-04-12 13:00 | 2020-04-14 17:00 | 3 dias
1.4.1 | Pruebas de servidor | 2020-04-12 13:00 | 2020-04-12 17:00 | 1 dia
1.4.2 | Pruebas del simulador | 2020-04-13 13:00 | 2020-04-13 17:00 | 1 dia
1.4.3 | Pruebas del cliente | 2020-04-14 13:00 | 2020-04-14 17:00 | 1 dia

## TempData (hidden)
Work- | Baseline Work- | Actual Work- | Work Variance- | Remaining Work- | Cost- | Baseline Cost- | Actual Cost- | Fixed Cost- | Cost Variance- | Remaining Cost- | BCWP- | BCWS- | SV- | Name+ | Notes+ | WBS+ | Constraint Type+ | Constraint Date= | Critical+ | Delay- | Free Slack- | Total Slack- | ID- | Milestone+ | Priority+ | Subproject+ | Baseline Duration- | Actual Duration- | Duration- | Duration Variance- | Remaining Duration- | Percent Complete-[% Complete] | Percent Work Complete-[% Work Complete] | Start= | Finish= | Early Start= | Early Finish= | Late Start= | Late Finish= | Actual Start= | Actual Finish= | Baseline Start= | Baseline Finish= | Start Variance- | Finish Variance- | Predecessors+ | Successors+ | Resource Names+ | Resource Initials+ | Text1+ | Start1= | Finish1= | Text2+ | Start2= | Finish2= | Text3+ | Start3= | Finish3= | Text4+ | Start4= | Finish4= | Text5+ | Start5= | Finish5= | Text6+ | Text7+ | Text8+ | Text9+ | Text10+ | Marked+ | Flag1+ | Flag2+ | Flag3+ | Flag4+ | Flag5+ | Flag6+ | Flag7+ | Flag8+ | Flag9+ | Flag10+ | Rollup+ | CV- | Project+ | Outline Level- | Unique ID- | Number1- | Number2- | Number3- | Number4- | Number5- | Summary+ | Created= | Unique ID Predecessors+ | Unique ID Successors+ | Objects- | Linked Fields+ | Resume= | Stop= | Resume No Earlier Than= | Outline Number+ | Duration1- | Duration2- | Duration3- | Cost1- | Cost2- | Cost3- | Hide Bar+ | Confirmed+ | Update Needed+ | Contact+ | Resource Group+ | ACWP- | Type+ | Recurring+ | Effort Driven+ | Overtime Work- | Actual Overtime Work- | Remaining Overtime Work- | Regular Work- | Overtime Cost- | Actual Overtime Cost- | Remaining Overtime Cost- | Fixed Cost Accrual+ | Hyperlink+ | Hyperlink Address+ | Hyperlink SubAddress+ | Hyperlink Href+ | Assignment+ | Overallocated+ | External Task+ | Subproject Read Only+ | Response Pending+ | TeamStatus Pending+ | Leveling Can Split+ | Level Assignments+ | Work Contour+ | Cost4- | Cost5- | Cost6- | Cost7- | Cost8- | Cost9- | Cost10- | Date1= | Date2= | Date3= | Date4= | Date5= | Date6= | Date7= | Date8= | Date9= | Date10= | Duration4- | Duration5- | Duration6- | Duration7- | Duration8- | Duration9- | Duration10- | Start6= | Finish6= | Start7= | Finish7= | Start8= | Finish8= | Start9= | Finish9= | Start10= | Finish10= | Flag11+ | Flag12+ | Flag13+ | Flag14+ | Flag15+ | Flag16+ | Flag17+ | Flag18+ | Flag19+ | Flag20+ | Number6- | Number7- | Number8- | Number9- | Number10- | Number11- | Number12- | Number13- | Number14- | Number15- | Number16- | Number17- | Number18- | Number19- | Number20- | Text11+ | Text12+ | Text13+ | Text14+ | Text15+ | Text16+ | Text17+ | Text18+ | Text19+ | Text20+ | Text21+ | Text22+ | Text23+ | Text24+ | Text25+ | Text26+ | Text27+ | Text28+ | Text29+ | Text30+ | Assignment Delay- | Assignment Units- | Cost Rate Table+ | Preleveled Start= | Preleveled Finish= | WBS Predecessors+ | WBS Successors+ | Deadline= | Outline Code1+ | Outline Code2+ | Outline Code3+ | Outline Code4+ | Outline Code5+ | Outline Code6+ | Outline Code7+ | Outline Code8+ | Outline Code9+ | Outline Code10+ | Status+ | Physical Percent Complete-[Physical % Complete] | SVPercent- | CVPercent- | Calendar+
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Proyecto Hotel |  | 1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 1 | No | Mínima |  | 0d | 0d | 24.5d | 24.5d | 24.5d | 0% | 0% | 2020-03-13 13:00 | 2020-04-30 17:00 | 2020-03-13 13:00 | 2020-04-30 17:00 | 2020-03-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Analisis |  | 1.1 | Lo antes posible |  | No | 0d | 21.5d | 21.5d | 2 | No | Mínima |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2020-03-13 13:00 | 2020-03-18 17:00 | 2020-03-13 13:00 | 2020-03-18 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 24 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Topicos (Historias de usuario) |  | 1.1.1 | No finalizar antes del | 2020-03-14 17:00 | No | 0d | 23.5d | 23.5d | 3 | No | Mínima |  | 0d | 0d | 1d | 1d | 2d | 0% | 0% | 2020-03-13 13:00 | 2020-03-14 17:00 | 2020-03-13 13:00 | 2020-03-14 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 28 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Requerimientos |  | 1.1.2 | No finalizar antes del | 2020-03-16 17:00 | No | 0d | 22.5d | 22.5d | 4 | No | Mínima |  | 0d | 0d | 1d | 1d | 2d | 0% | 0% | 2020-03-15 13:00 | 2020-03-16 17:00 | 2020-03-15 13:00 | 2020-03-16 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 25 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arquitectura |  | 1.1.3 | No finalizar antes del | 2020-03-18 17:00 | No | 0d | 21.5d | 21.5d | 5 | No | Mínima |  | 0d | 0d | 1d | 1d | 2d | 0% | 0% | 2020-03-17 13:00 | 2020-03-18 17:00 | 2020-03-17 13:00 | 2020-03-18 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 27 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.1.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Diseño |  | 1.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 6 | No | Mínima |  | 0d | 0d | 21.5d | 21.5d | 21.5d | 0% | 0% | 2020-03-19 13:00 | 2020-04-30 17:00 | 2020-03-19 13:00 | 2020-04-30 17:00 | 2020-03-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 30 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Servidor |  | 1.2.1 | Lo antes posible |  | No | 0d | 17.5d | 17.5d | 7 | No | Mínima |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2020-03-19 13:00 | 2020-03-26 17:00 | 2020-03-19 13:00 | 2020-03-26 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 31 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Eleccion de tecnologias (Sockets o RMI) |  | 1.2.1.1 | Lo antes posible |  | No | 0d | 20.5d | 20.5d | 8 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2020-03-19 13:00 | 2020-03-20 17:00 | 2020-03-19 13:00 | 2020-03-20 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 32 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.2.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prototipo de tecnologia a usar |  | 1.2.1.1.1 | No finalizar antes del | 2020-03-20 17:00 | No | 0d | 20.5d | 20.5d | 9 | No | Mínima |  | 0d | 0d | 1d | 1d | 2d | 0% | 0% | 2020-03-19 13:00 | 2020-03-20 17:00 | 2020-03-19 13:00 | 2020-03-20 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 5 | 33 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.1.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prototipo de manejo de hilos |  | 1.2.1.2 | No finalizar antes del | 2020-03-22 17:00 | No | 0d | 19.5d | 19.5d | 10 | No | Mínima |  | 0d | 0d | 1d | 1d | 2d | 0% | 0% | 2020-03-21 13:00 | 2020-03-22 17:00 | 2020-03-21 13:00 | 2020-03-22 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 34 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prototipo de metodos de comunicacion |  | 1.2.1.3 | No finalizar antes del | 2020-03-24 17:00 | No | 0d | 18.5d | 18.5d | 11 | No | Mínima |  | 0d | 0d | 1d | 1d | 2d | 0% | 0% | 2020-03-23 13:00 | 2020-03-24 17:00 | 2020-03-23 13:00 | 2020-03-24 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 35 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.1.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prototipo de un servidor bidireccional |  | 1.2.1.4 | No finalizar antes del | 2020-03-26 17:00 | No | 0d | 17.5d | 17.5d | 12 | No | Mínima |  | 0d | 0d | 1d | 1d | 2d | 0% | 0% | 2020-03-25 13:00 | 2020-03-26 17:00 | 2020-03-25 13:00 | 2020-03-26 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 36 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.1.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Simulador |  | 1.2.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 13 | No | Mínima |  | 0d | 0d | 17.5d | 17.5d | 17.5d | 0% | 0% | 2020-03-27 13:00 | 2020-04-30 17:00 | 2020-03-27 13:00 | 2020-04-30 17:00 | 2020-03-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 37 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.2.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prototipo de implementacion de un protocolo |  | 1.2.2.1 | No finalizar antes del | 2020-03-28 17:00 | No | 0d | 16.5d | 16.5d | 14 | No | Mínima |  | 0d | 0d | 1d | 1d | 2d | 0% | 0% | 2020-03-27 13:00 | 2020-03-28 17:00 | 2020-03-27 13:00 | 2020-03-28 17:00 | 2020-04-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 38 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prototipo de un programa en un hilo de ejecucion |  | 1.2.2.2 | No finalizar antes del | 2020-04-30 17:00 | Sí | 0d | 0d | 0d | 15 | No | Mínima |  | 0d | 0d | 16.5d | 16.5d | 2d | 0% | 0% | 2020-03-29 13:00 | 2020-04-30 17:00 | 2020-03-29 13:00 | 2020-04-30 17:00 | 2020-03-29 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 39 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.2.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Desarrollo |  | 1.3 | Lo antes posible |  | No | 0d | 9.5d | 9.5d | 16 | No | Mínima |  | 0d | 0d | 6d | 6d | 6d | 0% | 0% | 2020-03-31 13:00 | 2020-04-11 17:00 | 2020-03-31 13:00 | 2020-04-11 17:00 | 2020-04-27 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 42 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Servidor |  | 1.3.1 | No finalizar antes del | 2020-04-03 17:00 | No | 0d | 13.5d | 13.5d | 17 | No | Mínima |  | 0d | 0d | 2d | 2d | 4d | 0% | 0% | 2020-03-31 13:00 | 2020-04-03 17:00 | 2020-03-31 13:00 | 2020-04-03 17:00 | 2020-04-27 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 43 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Simulador |  | 1.3.2 | No finalizar antes del | 2020-04-07 17:00 | No | 0d | 11.5d | 11.5d | 18 | No | Mínima |  | 0d | 0d | 2d | 2d | 4d | 0% | 0% | 2020-04-04 13:00 | 2020-04-07 17:00 | 2020-04-04 13:00 | 2020-04-07 17:00 | 2020-04-27 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 44 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cliente |  | 1.3.3 | No finalizar antes del | 2020-04-11 17:00 | No | 0d | 9.5d | 9.5d | 19 | No | Mínima |  | 0d | 0d | 2d | 2d | 4d | 0% | 0% | 2020-04-08 13:00 | 2020-04-11 17:00 | 2020-04-08 13:00 | 2020-04-11 17:00 | 2020-04-27 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 46 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pruebas |  | 1.4 | Lo antes posible |  | No | 0d | 8d | 8d | 20 | No | Mínima |  | 0d | 0d | 1.5d | 1.5d | 1.5d | 0% | 0% | 2020-04-12 13:00 | 2020-04-14 17:00 | 2020-04-12 13:00 | 2020-04-14 17:00 | 2020-04-30 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 49 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pruebas de servidor |  | 1.4.1 | No finalizar antes del | 2020-04-12 17:00 | No | 0d | 9d | 9d | 21 | No | Mínima |  | 0d | 0d | 0.5d | 0.5d | 0d | 0% | 0% | 2020-04-12 13:00 | 2020-04-12 17:00 | 2020-04-12 13:00 | 2020-04-12 17:00 | 2020-04-30 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 52 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.4.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pruebas del simulador |  | 1.4.2 | No finalizar antes del | 2020-04-13 17:00 | No | 0d | 8.5d | 8.5d | 22 | No | Mínima |  | 0d | 0d | 0.5d | 0.5d | 0d | 0% | 0% | 2020-04-13 13:00 | 2020-04-13 17:00 | 2020-04-13 13:00 | 2020-04-13 17:00 | 2020-04-30 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 53 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.4.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pruebas del cliente |  | 1.4.3 | No finalizar antes del | 2020-04-14 17:00 | No | 0d | 8d | 8d | 23 | No | Mínima |  | 0d | 0d | 0.5d | 0.5d | 0d | 0% | 0% | 2020-04-14 13:00 | 2020-04-14 17:00 | 2020-04-14 13:00 | 2020-04-14 17:00 | 2020-04-30 13:00 | 2020-04-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 54 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.4.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Calendario Proyecto)